## Sheet1
App Area | Description | Severity | Type | Assigned To | Status | Details
Login Page | Register button width should be the length of the two login buttons | Minor | Code |  | Completed
Login Page | Spinner needs to come in the center | Minor | Code |  | Completed
Login Page | Validation error text needs to come below or alongside the text boxes | Minor | Code |  | Completed
Registration Page | Select profile image button is not User Friendly, User tries to click the | Minor | Code
Registration Page | Pre populate country code and provide in a drop dowon(Minor) | Minor | Code |  | Completed
Registration Page | Mobile Number validation does not work properly(Major) The application crashed 3 times. It seems there is an index out of bounds exception in the mobile number validator. Refer details for log | Major | Code |  | Completed | java.lang.RuntimeException: java.lang.reflect.InvocationTargetException at com.android.internal.os.ZygoteInit.main(ZygoteInit.java:1120) Caused by: java.lang.reflect.InvocationTargetException at java.lang.reflect.Method.invoke(Native Method) at com.android.internal.os.ZygoteInit$MethodAndArgsCaller.run(ZygoteInit.java:1230) ... 1 more Caused by: android.runtime.JavaProxyThrowable: System.ArgumentOutOfRangeException: Index was out of range. Must be non-negative and less than the size of the collection. Parameter name: index at System.ThrowHelper.ThrowArgumentOutOfRangeException (ExceptionArgument argument, ExceptionResource resource) <0x92db0140 + 0x00038> in <filename unknown>:0 at System.ThrowHelper.ThrowArgumentOutOfRangeException () <0x92db0118 + 0x0000f> in <filename unknown>:0 at System.Collections.Generic.List`1[T].get_Item (Int32 index) <0xb32143f8 + 0x00027> in <filename unknown>:0 at System.Collections.ObjectModel.Collection`1[T].get_Item (Int32 index) <0xa8928d78 + 0x00047> in <filename unknown>:0 at RideShare.RegisterPage.MobileNumberValidator () <0x92dafc58 + 0x00087> in <filename unknown>:0 at RideShare.RegisterPage.mobileNumberEntry_Unfocused (System.Object sender, Xamarin.Forms.FocusEventArgs e) <0x92dafba8 + 0x00063> in <filename unknown>:0 at Xamarin.Forms.VisualElement.OnUnfocus () <0x92dafaa8 + 0x0004b> in <filename unknown>:0 at Xamarin.Forms.VisualElement.OnIsFocusedPropertyChanged (Xamarin.Forms.BindableObject bindable, System.Object oldvalue, System.Object newvalue) <0x92dae000 + 0x000a3> in <filename unknown>:0 at Xamarin.Forms.BindableObject.SetValueActual (Xamarin.Forms.BindableProperty property, Xamarin.Forms.BindablePropertyContext context, System.Object value, Boolean currentlyApplying, SetValueFlags attributes, Boolean silent) <0xaeadebd0 + 0x0029f> in <filename unknown>:0 at Xamarin.Forms.BindableObject.SetValueCore (Xamarin.Forms.BindableProperty property, System.Object value, SetValueFlags attributes, SetValuePrivateFlags privateAttributes) <0xaeadd5e8 + 0x002eb> in <filename unknown>:0 at Xamarin.Forms.BindableObject.SetValueCore (Xamarin.Forms.BindablePropertyKey propertyKey, System.Object value, SetValueFlags attributes) <0x935bdad0 + 0x0003b> in <filename unknown>:0 at Xamarin.Forms.Element.Xamarin.Forms.IElementController.SetValueFromRenderer (Xamarin.Forms.BindablePropertyKey property, System.Object value) <0x935bda78 + 0x00027> in <filename unknown>:0 at Xamarin.Forms.Platform.Android.ViewRenderer`2[TView,TNativeView].Android.Views.View.IOnFocusChangeListener.OnFocusChange (Android.Views.View v, Boolean hasFocus) <0x939d5b50 + 0x002e7> in <filename unknown>:0 at Android.Views.View+IOnFocusChangeListenerInvoker.n_OnFocusChange_Landroid_view_View_Z (IntPtr jnienv, IntPtr native__this, IntPtr native_v, Boolean hasFocus) <0x939d5aa8 + 0x0006b> in <filename unknown>:0 at (wrapper dynamic-method) System.Object:ad85bd3a-d308-4a45-af1b-34295de771c5 (intptr,intptr,intptr,bool) --- End of stack trace from previous location where exception was thrown --- at System.Runtime.ExceptionServices.ExceptionDispatchInfo.Throw () <0x92db4928 + 0x00024> in <filename unknown>:0 at Java.Interop.JniEnvironment+InstanceMethods.CallVoidMethod (JniObjectReference instance, Java.Interop.JniMethodInfo method, Java.Interop.JniArgumentValue* args) <0xaeb392b8 + 0x000af> in <filename unknown>:0 at Java.Interop.JniPeerMembers+JniInstanceMethods.InvokeVirtualVoidMethod (System.String encodedMember, IJavaPeerable self, Java.Interop.JniArgumentValue* parameters) <0xb31dfb78 + 0x00087> in <filename unknown>:0 at Android.Views.View.ClearFocus () <0x92daf9f0 + 0x00043> in <filename unknown>:0 at Xamarin.Forms.Platform.Android.PlatformRenderer.DispatchTouchEvent (Android.Views.MotionEvent e) <0x92ea3a70 + 0x0065b> in <filename unknown>:0 at Android.Views.View.n_DispatchTouchEvent_Landroid_view_MotionEvent_ (IntPtr jnienv, IntPtr native__this, IntPtr native_e) <0x92ea3858 + 0x0005b> in <filename unknown>:0 at (wrapper dynamic-method) System.Object:5e195528-53f3-4de5-acaf-1ea83fa9e0c9 (intptr,intptr,intptr) at md5b60ffeb829f638581ab2bb9b1a7f4f3f.PlatformRenderer.n_dispatchTouchEvent(Native Method) at md5b60ffeb829f638581ab2bb9b1a7f4f3f.PlatformRenderer.dispatchTouchEvent(PlatformRenderer.java:47) at android.view.ViewGroup.dispatchTransformedTouchEvent(ViewGroup.java:2841) at android.view.ViewGroup.dispatchTouchEvent(ViewGroup.java:2516) at android.view.ViewGroup.dispatchTransformedTouchEvent(ViewGroup.java:2841) at android.view.ViewGroup.dispatchTouchEvent(ViewGroup.java:2516) at android.view.ViewGroup.dispatchTransformedTouchEvent(ViewGroup.java:2841) at android.view.ViewGroup.dispatchTouchEvent(ViewGroup.java:2516) at android.view.ViewGroup.dispatchTransformedTouchEvent(ViewGroup.java:2841) at android.view.ViewGroup.dispatchTouchEvent(ViewGroup.java:2516) at com.android.internal.policy.PhoneWindow$DecorView.superDispatchTouchEvent(PhoneWindow.java:2795) at com.android.internal.policy.PhoneWindow.superDispatchTouchEvent(PhoneWindow.java:1848) at android.app.Activity.dispatchTouchEvent(Activity.java:3047) at com.android.internal.policy.PhoneWindow$DecorView.dispatchTouchEvent(PhoneWindow.java:2756) at android.view.View.dispatchPointerEvent(View.java:10229) at android.view.ViewRootImpl$ViewPostImeInputStage.processPointerEvent(ViewRootImpl.java:5357) at android.view.ViewRootImpl$ViewPostImeInputStage.onProcess(ViewRootImpl.java:5193) at android.view.ViewRootImpl$InputStage.deliver(ViewRootImpl.java:4633) at android.view.ViewRootImpl$InputStage.onDeliverToNext(ViewRootImpl.java:4686) at android.view.ViewRootImpl$InputStage.forward(ViewRootImpl.java:4652) at android.view.ViewRootImpl$AsyncInputStage.forward(ViewRootImpl.java:4794) at android.view.ViewRootImpl$InputStage.apply(ViewRootImpl.java:4660) at android.view.ViewRootImpl$AsyncInputStage.apply(ViewRootImpl.java:4851) at android.view.ViewRootImpl$InputStage.deliver(ViewRootImpl.java:4633) at android.view.ViewRootImpl$InputStage.onDeliverToNext(ViewRootImpl.java:4686) at android.view.ViewRootImpl$InputStage.forward(ViewRootImpl.java:4652) at android.view.ViewRootImpl$InputStage.apply(ViewRootImpl.java:4660) at android.view.ViewRootImpl$InputStage.deliver(ViewRootImpl.java:4633) at android.view.ViewRootImpl.deliverInputEvent(ViewRootImpl.java:7330) at android.view.ViewRootImpl.doProcessInputEvents(ViewRootImpl.java:7208) at android.view.ViewRootImpl.enqueueInputEvent(ViewRootImpl.java:7169) at android.view.ViewRootImpl$WindowInputEventReceiver.onInputEvent(ViewRootImpl.java:7440) at android.view.InputEventReceiver.dispatchInputEvent(InputEventReceiver.java:185) at android.os.MessageQueue.nativePollOnce(Native Method) at android.os.MessageQueue.next(MessageQueue.java:323) at android.os.Looper.loop(Looper.java:143) at android.app.ActivityThread.main(ActivityThread.java:7231)
Forgot Password | When you click next, a spinner needs to appear | Minor | Code |  | Completed
Documentation | How to create and APK file section needs to be added to Developer Guide | Minor | Documentation |  | Completed
Forgot Password | Bring the contents of the forgot password page to middle, decrease the button width |  | Code |  | Completed
Registration Completion | Bring the contents of the registration completion page to middle, decrease the button width |  | Code |  | Completed
App | Standardize the buttons throughout the app (base login page buttons) |  | Code |  | Completed
Menu | Remove the duplicate icon and add a new one |  | Code |  | Completed
Register Page/Edit Profile | Need to show the flag + Country name in the country code picking section of the phone number as the user experience is not good. Might need to change the control to a ListView from a picker. Refer to the Uber country code viewer. https://developer.xamarin.com/api/type/Xamarin.Forms.ListView/ | Medium | Functional |  | Open
Register Page/Edit Profile |  | Medium | Code |  | Open
Login Page | When the application is closed, need to always sign in. Which is a bad user experience | Medium | User Experience |  | As design | The services will be running, even if the user swips and closes the app. The services will try to access the app, but since the app has been closed, continues error messages will pop up. As a fix for this when the user swips the app, (s)he will be logged out, services are stopped and a notification will be sent through UrbanAirship to that specific user and all his/her ride-contacts. | -
Login Page | Even after Dimuth cleared his application data, it shows an old user name pre-populated as the user name | Medium | Data |  | As design | When a user registers for the first time, the device id will also be stored along with the user details. When the user tries to log in again, the user id will be retreived from that device id. This is for a better user experience. | -
Orphaned Data | Test data, several of Sithira's users appear on the map all the time | Medium | Data |  | Open
About Page | Include Application Version | Medium | User Experience |  | Completed
Map | Try to set the current location in the map, so that it loads that first as apposed to loading Rome and then navigating | Medium | User Experience |  | Open
Getting a ride | Selecting a driver to request a ride is not very intutive, may be we might need a button like "Request Ride" on that popup | Medium | User Experience
Map | Riders and Drivers don't seem to get updated on the map at times
Application | When application crashes, the user needs to be logged out. Otherwise there will be orphan users in the map. |  | Functional |  | Open
Application | When user presses back button, the user is logged out. This is a bad user experience. User should not need to login again. |  | User Experience |  | Completed